## ELECTORAL OFFICER
FOR THE BY-ELECTION OF TWO (2) COUNCILLORS

### Introduction

Nak’azdli Whut’en Chief and Council are requesting proposals for the services of an Electoral Officer to oversee the upcoming by-election for two (2) Council seats in accordance with the Nak’azdli Whut’en Custom Election Code 2019.

### Scope Of Work

The successful proponent will:

- Issue a call for by-election a minimum of 45 days before election day, per Section 3.1(e).

- Develop and manage the pre-election timeline, ensuring adherence to all Code-mandated procedures, adjusting timelines as appropriate for a by-election.

- Organize and supervise all stages of the election process, including:

  - Nomination meeting and public notice process.

  - Verification of candidate eligibility.

  - Voter registration and maintenance of the Voter List.

  - Coordination and training of polling staff and volunteers.

  - Management of polling stations in Fort St. James, Prince George, and Vancouver, BC.

  - Distribution of 975 mail-in ballots to off-reserve members and secure ballot tracking.

  - Maintenance of privacy and integrity of all votes cast (mail-in, advance, and in-person).

  - Setup and supervision of polling stations from 8:00 a.m. to 8:00 p.m. PST on Election Day.

  - Supervised vote tabulation and public declaration of results.

  - Documentation and secure storage of all election materials for one year or until legal matters are resolved.

  - Collaboration with the Election Appeal Board, if appointed.

  - Production and submission of an Electoral Officer Certificate upon completion.

- Ensure compliance with the Oath of Electoral Officer & Assistants as required by the Code.

- Maintain clear and open communication with Nak’azdli Whut’en throughout the process.

### Proposal Submission Instructions

- Proposals must be received by noon PST on Tuesday, April 15, 2025.

- Sealed proposals must clearly indicate:
“RFP for Electoral Officer” and include the name of the proponent.

- Late submissions will be returned unopened.

- Proposals submitted via fax or email will not be accepted.

- Proposals should include:

### Required Proposal Contents

- Executive Summary

  - Description of proponent’s company or personal background

  - Overview of contents and any exceptions to requirements

- Qualifications

  - Proven experience as an Electoral Officer or in a related role

  - Familiarity with First Nations election processes

  - Strong organizational, communication, and conflict resolution skills

  - Understanding of relevant electoral laws and regulations

- Project Team (if applicable)

  - Team composition, roles, and experience

  - Specific experience with Nak’azdli Whut’en or other First Nations elections

- Declaration & Warranty

  - Commitment to abide by the Nak’azdli Whut’en Custom Election Code 2019

- References

  - Contact information for three (3) recent clients who have used the proponent’s electoral services

- Cost Breakdown

  - Detailed pricing including administration, travel, materials, printing, translation, and other costs

  - Total project cost must be stated in Canadian Dollars and be fixed price

- Consultation Fee Estimate

  - Daily rate and estimated time required for services

### Contact For Clarifications

### All questions or requests for clarification must be directed to:

Tracey Baldwin
Executive Assistant to the COO
Nak’azdli Whut’en
Box 1329
Fort St. James, BC V0J 1P0
(250) 996-7171
tracey.baldwin@nakazdliwhuten.ca